## README
NileCrop — Project Master Plan
AI-Powered Crop Recommendation & Disease Detection ¦ Delta University 2025-26
📋 SHEETS IN THIS FILE
Week 1 | Setup, Backend skeleton, Crop Model (DONE ✅)
Week 2 | Disease Model, Backend APIs, Frontend init
Week 3 | Full integration, Arabic support, PWA
Week 4 | Testing, bug fixes, deployment
Week 5 | Final polish, documentation, presentation
GitHub Structure | Branches, protection rules, PR workflow
Task Locking Rules | How tasks get locked when done
📌 STATUS LEGEND
⬜ Not Started | Task hasn't been touched yet
🔄 In Progress | Currently being worked on
✅ Done | Completed — file locked on GitHub
❌ Blocked | Can't continue — notify Team Leader
🔒 Locked | Merged to main — READ ONLY
⚙️ LOCKING RULES
Rule 1 | When a task is DONE → open PR on GitHub → Team Leader reviews
Rule 2 | After PR is merged → status changes to LOCKED 🔒
Rule 3 | LOCKED files cannot be edited without Team Leader approval
Rule 4 | Each person works ONLY on their assigned branch
Rule 5 | NEVER push directly to main — always via Pull Request

## Week 1
NileCrop — Week 1 Tasks
Focus: Setup, Architecture, Backend Skeleton, Crop Model (Most tasks DONE ✅)
Task ID | Task Name | Role | Priority | Branch | File Path on GitHub | Local Path (D:\Projects\...) | Depends On | Assigned To | Status | Done Date | Notes
👑 Team Leader
TL-01 | GitHub Repo Setup & Branch Protection | TL | 🔴 | main | Repo itself | D:\Projects\smart-crop-assistant\ | — | Team Leader | 🔒 Locked | 🔒 | DONE ✅ — 6 branches + 9 members
TL-02 | Architecture Diagram | TL | 🔴 | main | docs/architecture.png | D:\Projects\smart-crop-assistant\Docs\ | — | Team Leader | ⬜ Not Started |  | System flow: React→FastAPI→PostgreSQL+AI+APIs
TL-03 | ERD — Database Design | TL | 🔴 | main | docs/erd.png | D:\Projects\smart-crop-assistant\Docs\ | TL-02 | Team Leader | ⬜ Not Started |  | Tables: cities, crop_requests, disease_requests, disease_info
⚙️ Backend
BE-01 | PostgreSQL Setup + Config | BE | 🔴 | feature/backend | Backend/config.py + Backend/database.py | D:\Projects\smart-crop-assistant\Backend\ | TL-03 | Backend | ⬜ Not Started |  | Connection + SQLAlchemy ORM
BE-02 | FastAPI Main + Health Endpoint | BE | 🔴 | feature/backend | Backend/main.py | D:\Projects\smart-crop-assistant\Backend\ | BE-01 | Backend | ⬜ Not Started |  | GET /health → {status:ok}. CORS + JWT setup
BE-03 | Cities Table + 60 Cities Seed | BE | 🔴 | feature/backend | Backend/models/city.py + Backend/seed_cities.py | D:\Projects\smart-crop-assistant\Backend\models\ | BE-01 | Backend | ⬜ Not Started |  | seed_cities.py already exists ✅
BE-04 | External APIs Integration | BE | 🔴 | feature/backend | Backend/routers/weather.py + soil.py | D:\Projects\smart-crop-assistant\Backend\routers\ | BE-02 | Backend | ⬜ Not Started |  | Open-Meteo (weather) + SoilGrids (soil) + NASA POWER
🤖 AI / ML
AI-01 | Crop Dataset EDA | AI | 🔴 | feature/crop-model | ai-ml/notebooks/crop_eda.ipynb | D:\Projects\smart-crop-assistant\ai-ml\notebooks\ | — | AI Team | 🔒 Locked | 🔒 | DONE ✅ — 2200 rows, 21 Egyptian crops
AI-02 | Data Preprocessing | AI | 🔴 | feature/crop-model | ai-ml/models/scaler.pkl + label_encoder.pkl | D:\Projects\smart-crop-assistant\ai-ml\models\ | AI-01 | AI Team | 🔒 Locked | 🔒 | DONE ✅ — scaler + encoder saved
AI-03 | Train Random Forest Model | AI | 🔴 | feature/crop-model | ai-ml/models/crop_model.pkl | D:\Projects\smart-crop-assistant\ai-ml\models\ | AI-02 | AI Team | 🔒 Locked | 🔒 | DONE ✅ — 99.55% accuracy
AI-04 | Crop Recommend API Endpoint | AI | 🔴 | feature/crop-model | Backend/routers/recommend.py | D:\Projects\smart-crop-assistant\Backend\routers\ | AI-03,BE-04 | AI Team | ⬜ Not Started |  | POST /recommend → city → auto-fetch data → crop + confidence%
✏️ UI / UX
UX-01 | Color Palette + Typography | UX | 🟡 | — | Figma (share link) | Figma | — | UI/UX | ⬜ Not Started |  | Primary: #22c55e, Dark: #0F172A, Font: Cairo
UX-02 | User Flow Diagram | UX | 🔴 | main | docs/user-flow.png | D:\Projects\smart-crop-assistant\Docs\ | UX-01 | UI/UX | ⬜ Not Started |  | Already have user-flow.html ✅ — export as PNG
🧪 Testing & Docs
QA-01 | Requirements Files | QA | 🟡 | feature/backend | Backend/requirements.txt | D:\Projects\smart-crop-assistant\Backend\ | BE-02 | QA | ⬜ Not Started |  | All Python + Node dependencies listed
Week 1 Summary: Total Tasks = 14 ¦ Already Done = 4 ¦ Remaining = 10

## Week 2
NileCrop — Week 2 Tasks
Focus: Disease Model Training, Backend APIs, Frontend Init
Task ID | Task Name | Role | Priority | Branch | File Path on GitHub | Local Path (D:\Projects\...) | Depends On | Assigned To | Status | Done Date | Notes
🤖 AI / ML
AI-05 | PlantVillage Dataset (17 classes subset) | AI | 🔴 | feature/disease-model | ai-ml/notebooks/disease_eda.ipynb | D:\Projects\smart-crop-assistant\ai-ml\notebooks\ | — | AI Team | ⬜ Not Started |  | <10,000 images, 17 disease classes for 21 Egyptian crops
AI-06 | Image Preprocessing Pipeline | AI | 🔴 | feature/disease-model | ai-ml/notebooks/data_pipeline.py | D:\Projects\smart-crop-assistant\ai-ml\notebooks\ | AI-05 | AI Team | ⬜ Not Started |  | Resize 224x224 + normalize + augment (flip, rotate, brightness)
AI-07 | MobileNetV2 Architecture Setup | AI | 🔴 | feature/disease-model | ai-ml/notebooks/mobilenetv2_setup.ipynb | D:\Projects\smart-crop-assistant\ai-ml\notebooks\ | AI-06 | AI Team | ⬜ Not Started |  | Transfer learning — ImageNet weights, freeze base layers
AI-08 | Train CNN Disease Model v1 | AI | 🔴 | feature/disease-model | ai-ml/models/disease_model.h5 | D:\Projects\smart-crop-assistant\ai-ml\models\ | AI-07 | AI Team | ⬜ Not Started |  | Target: >90% accuracy, 17 classes
AI-09 | Fine-tune CNN Model v2 | AI | 🔴 | feature/disease-model | ai-ml/models/disease_model_v2.h5 | D:\Projects\smart-crop-assistant\ai-ml\models\ | AI-08 | AI Team | ⬜ Not Started |  | Unfreeze last 20 layers, lr=0.0001 — target ~94%
⚙️ Backend
BE-05 | Disease Info Table + 17 Records | BE | 🔴 | feature/backend | Backend/models/disease_info.py | D:\Projects\smart-crop-assistant\Backend\models\ | BE-01 | Backend | ⬜ Not Started |  | Arabic disease names + treatment for 17 classes
BE-06 | Request Logging Tables | BE | 🟡 | feature/backend | Backend/models/crop_request.py + disease_request.py | D:\Projects\smart-crop-assistant\Backend\models\ | BE-01 | Backend | ⬜ Not Started |  | Log every request for analytics
BE-07 | City Search Endpoint | BE | 🔴 | feature/backend | Backend/routers/cities.py | D:\Projects\smart-crop-assistant\Backend\routers\ | BE-03 | Backend | ⬜ Not Started |  | GET /cities?q= → search in Arabic + English
BE-08 | Image Upload Handler | BE | 🔴 | feature/backend | Backend/routers/upload.py | D:\Projects\smart-crop-assistant\Backend\routers\ | BE-02 | Backend | ⬜ Not Started |  | Accept JPG/PNG ≤5MB, save temp, pass to AI
BE-09 | Geocoding Service | BE | 🟡 | feature/backend | Backend/services/geocoding.py | D:\Projects\smart-crop-assistant\Backend\services\ | BE-04 | Backend | ⬜ Not Started |  | OSM Nominatim: city name → lat/lon
🎨 Frontend
FE-01 | React Project Init (Vite + Tailwind) | FE | 🔴 | feature/frontend | Frontend/ | D:\Projects\smart-crop-assistant\Frontend\ | — | Frontend | ⬜ Not Started |  | Vite + React + Tailwind + axios + react-router-dom + Chart.js
FE-02 | Navbar + Language Toggle | FE | 🔴 | feature/frontend | Frontend/src/components/Navbar.jsx | D:\Projects\smart-crop-assistant\Frontend\src\components\ | FE-01 | Frontend | ⬜ Not Started |  | Arabic/English toggle — RTL/LTR switch
FE-03 | Home Page Hero + 2 Buttons | FE | 🔴 | feature/frontend | Frontend/src/pages/Home.jsx | D:\Projects\smart-crop-assistant\Frontend\src\pages\ | FE-02 | Frontend | ⬜ Not Started |  | Hero + 'Get Crop' button + 'Detect Disease' button
✏️ UI / UX
UX-03 | Wireframes — 4 Screens | UX | 🔴 | — | Figma | Figma | UX-01 | UI/UX | ⬜ Not Started |  | Home, Crop Modal, Disease Modal, Result Screen
UX-04 | Hi-Fi Mockups — All Screens | UX | 🔴 | — | Figma | Figma | UX-03 | UI/UX | ⬜ Not Started |  | Share Figma link with Frontend team
Week 2 Summary: Total Tasks = 15 ¦ Already Done = 0 ¦ Remaining = 15

## Week 3
NileCrop — Week 3 Tasks
Focus: Full Integration, Arabic RTL, PWA Setup
Task ID | Task Name | Role | Priority | Branch | File Path on GitHub | Local Path (D:\Projects\...) | Depends On | Assigned To | Status | Done Date | Notes
🤖 AI / ML
AI-10 | Disease API Endpoint | AI | 🔴 | feature/disease-model | Backend/routers/disease.py | D:\Projects\smart-crop-assistant\Backend\routers\ | AI-09,BE-08 | AI Team | ⬜ Not Started |  | POST /disease → image → 17-class CNN → Arabic result + treatment
AI-11 | Disease Lookup Service | AI | 🔴 | feature/disease-model | Backend/services/disease_lookup.py | D:\Projects\smart-crop-assistant\Backend\services\ | AI-10,BE-05 | AI Team | ⬜ Not Started |  | Map class name → Arabic disease info + treatment from DB
AI-12 | Convert to TFLite | AI | 🟡 | feature/disease-model | ai-ml/models/disease_model.tflite | D:\Projects\smart-crop-assistant\ai-ml\models\ | AI-09 | AI Team | ⬜ Not Started |  | int8 quantization — target <20MB for fast server response
⚙️ Backend
BE-10 | Validation + Error Handling | BE | 🔴 | feature/backend | Backend/schemas/ | D:\Projects\smart-crop-assistant\Backend\schemas\ | BE-02 | Backend | ⬜ Not Started |  | Pydantic models — clear error messages, no 500 crashes
BE-11 | CORS + Security + Rate Limiting | BE | 🔴 | feature/backend | Backend/main.py (update) | D:\Projects\smart-crop-assistant\Backend\ | BE-02 | Backend | ⬜ Not Started |  | Allow Vercel URL, block abuse
BE-12 | Analytics Endpoint | BE | 🟢 | feature/backend | Backend/routers/analytics.py | D:\Projects\smart-crop-assistant\Backend\routers\ | BE-06 | Backend | ⬜ Not Started |  | GET /analytics → top crops, top diseases, total requests
🎨 Frontend
FE-04 | Crop Recommendation Modal | FE | 🔴 | feature/frontend | Frontend/src/components/CropModal.jsx | D:\Projects\smart-crop-assistant\Frontend\src\components\ | FE-03,UX-04 | Frontend | ⬜ Not Started |  | City dropdown + search + loading spinner
FE-05 | Disease Detection Modal | FE | 🔴 | feature/frontend | Frontend/src/components/DiseaseModal.jsx | D:\Projects\smart-crop-assistant\Frontend\src\components\ | FE-03,UX-04 | Frontend | ⬜ Not Started |  | Drag & drop + click upload + image preview
FE-06 | Connect Crop to Backend (api.js) | FE | 🔴 | feature/frontend | Frontend/src/services/api.js | D:\Projects\smart-crop-assistant\Frontend\src\services\ | FE-04,AI-04 | Frontend | ⬜ Not Started |  | POST /recommend → show top-3 crops with confidence %
FE-07 | Connect Disease to Backend | FE | 🔴 | feature/frontend | Frontend/src/services/api.js (update) | D:\Projects\smart-crop-assistant\Frontend\src\services\ | FE-05,AI-10 | Frontend | ⬜ Not Started |  | POST /disease → show Arabic disease name + treatment
FE-08 | Result Cards (Crop + Disease) | FE | 🔴 | feature/frontend | Frontend/src/components/CropResult.jsx + DiseaseResult.jsx | D:\Projects\smart-crop-assistant\Frontend\src\components\ | FE-06,FE-07 | Frontend | ⬜ Not Started |  | Top-3 crops with %, disease + Arabic treatment + confidence
FE-09 | Arabic Translations (ar.json + en.json) | FE | 🔴 | feature/frontend | Frontend/src/locales/ar.json + en.json | D:\Projects\smart-crop-assistant\Frontend\src\locales\ | FE-02 | Frontend | ⬜ Not Started |  | Full RTL layout when Arabic selected
FE-10 | PWA Setup (manifest.json) | FE | 🟡 | feature/frontend | Frontend/public/manifest.json | D:\Projects\smart-crop-assistant\Frontend\public\ | FE-01 | Frontend | ⬜ Not Started |  | Installable on mobile, offline basic support
FE-11 | Geolocation Hook | FE | 🟡 | feature/frontend | Frontend/src/hooks/useGeolocation.js | D:\Projects\smart-crop-assistant\Frontend\src\hooks\ | FE-04 | Frontend | ⬜ Not Started |  | Auto-detect city from GPS
✏️ UI / UX
UX-05 | App Icon + Branding | UX | 🟡 | feature/frontend | Frontend/public/icons/ | D:\Projects\smart-crop-assistant\Frontend\public\icons\ | UX-01 | UI/UX | ⬜ Not Started |  | NileCrop icon — 16,32,192,512px
🧪 Testing & Docs
QA-02 | Manual API Testing — Postman Collection | QA | 🟡 | feature/backend | docs/postman-collection.json | D:\Projects\smart-crop-assistant\Docs\ | BE-10 | QA | ⬜ Not Started |  | Test all endpoints: health, cities, recommend, disease, analytics
Week 3 Summary: Total Tasks = 16 ¦ Already Done = 0 ¦ Remaining = 16

## Week 4
NileCrop — Week 4 Tasks
Focus: Testing, Bug Fixes, Deployment (Render + Vercel)
Task ID | Task Name | Role | Priority | Branch | File Path on GitHub | Local Path (D:\Projects\...) | Depends On | Assigned To | Status | Done Date | Notes
👑 Team Leader
TL-04 | Integration Test + Bug Report | TL | 🔴 | dev | docs/integration-test-report.md | D:\Projects\smart-crop-assistant\Docs\ | FE-09,AI-10 | Team Leader | ⬜ Not Started |  | Full flow: city → crop AND image → disease in Arabic
⚙️ Backend
BE-13 | Backend Unit Tests | BE | 🔴 | feature/backend | Tests/test_backend.py | D:\Projects\smart-crop-assistant\Tests\ | BE-10 | Backend | ⬜ Not Started |  | pytest — min 15 test cases, all PASSED
BE-14 | Backend Deploy on Render | BE | 🔴 | — | Render.com dashboard | Render.com | BE-13 | Backend | ⬜ Not Started |  | Web Service + PostgreSQL + env vars + AI models upload
🤖 AI / ML
AI-13 | AI Models Evaluation Report | AI | 🔴 | feature/disease-model | ai-ml/reports/evaluation.md | D:\Projects\smart-crop-assistant\ai-ml\reports\ | AI-12 | AI Team | ⬜ Not Started |  | RF: 99.55% ¦ CNN: ~94% — charts + confusion matrices
AI-14 | Model Versioning Registry | AI | 🟡 | feature/crop-model | ai-ml/models/model_registry.json | D:\Projects\smart-crop-assistant\ai-ml\models\ | AI-13 | AI Team | ⬜ Not Started |  | Track all model versions + accuracy
🎨 Frontend
FE-12 | Frontend Error Handling + Offline Mode | FE | 🔴 | feature/frontend | Frontend/src/components/ErrorBoundary.jsx | D:\Projects\smart-crop-assistant\Frontend\src\components\ | FE-09 | Frontend | ⬜ Not Started |  | Arabic error messages — no technical errors shown to user
FE-13 | Performance Optimization | FE | 🟡 | feature/frontend | Frontend/ | D:\Projects\smart-crop-assistant\Frontend\ | FE-12 | Frontend | ⬜ Not Started |  | Lazy loading + image compression — Lighthouse >90
FE-14 | Frontend Deploy on Vercel | FE | 🔴 | — | Vercel.com dashboard | Vercel.com | FE-13 | Frontend | ⬜ Not Started |  | VITE_API_URL = Render backend URL
🧪 Testing & Docs
QA-03 | Backend API Test Suite | QA | 🔴 | feature/backend | Tests/test_api.py | D:\Projects\smart-crop-assistant\Tests\ | BE-14 | QA | ⬜ Not Started |  | pytest — all endpoints on LIVE Render URL
QA-04 | E2E Testing | QA | 🔴 | dev | Tests/test_e2e.py | D:\Projects\smart-crop-assistant\Tests\ | FE-14 | QA | ⬜ Not Started |  | Full flow on live Vercel URL — crop + disease
QA-05 | Cross-Browser + Mobile Testing | QA | 🟡 | main | docs/cross-browser-report.md | D:\Projects\smart-crop-assistant\Docs\ | FE-14 | QA | ⬜ Not Started |  | Chrome Desktop, Chrome Android, Safari iPhone
✏️ UI / UX
UX-06 | Production UI Check vs Figma | UX | 🔴 | main | docs/production-ui-check.md | D:\Projects\smart-crop-assistant\Docs\ | FE-14 | UI/UX | ⬜ Not Started |  | Compare live app vs Figma — report differences
Week 4 Summary: Total Tasks = 12 ¦ Already Done = 0 ¦ Remaining = 12

## Week 5
NileCrop — Week 5 Tasks
Focus: Final Polish, Documentation, Presentation Prep
Task ID | Task Name | Role | Priority | Branch | File Path on GitHub | Local Path (D:\Projects\...) | Depends On | Assigned To | Status | Done Date | Notes
👑 Team Leader
TL-05 | Demo Script | TL | 🔴 | main | docs/demo-script.md | D:\Projects\smart-crop-assistant\Docs\ | TL-04 | Team Leader | ⬜ Not Started |  | Step-by-step script for Dr. Eman — max 10 min
TL-06 | Final Feature Freeze Announcement | TL | 🔴 | — | WhatsApp Group | WhatsApp | TL-04 | Team Leader | ⬜ Not Started |  | No new features — bugs + docs only
TL-07 | Final Submission Checklist + Send to Supervisor | TL | 🔴 | — | GitHub URL + Vercel URL | Send to Dr. Eman | ALL | Team Leader | ⬜ Not Started |  | GitHub URL + Vercel URL + README + Presentation
⚙️ Backend
BE-15 | Final Bug Fixes | BE | 🔴 | feature/backend | Backend/routers/ | D:\Projects\smart-crop-assistant\Backend\routers\ | QA-03 | Backend | ⬜ Not Started |  | Fix all Critical issues from testing
BE-16 | Production Health Check | BE | 🔴 | — | Render live URL | Render.com | BE-15 | Backend | ⬜ Not Started |  | All endpoints 200 OK on live URL
🤖 AI / ML
AI-15 | Live Demo Preparation | AI | 🔴 | — | Live URL + screenshots | Production URL | AI-13 | AI Team | ⬜ Not Started |  | 5 crop tests + 5 disease tests on live URL — backup screenshots
🎨 Frontend
FE-15 | UI Polish + Micro-animations | FE | 🟢 | feature/frontend | Frontend/src/ | D:\Projects\smart-crop-assistant\Frontend\src\ | FE-14 | Frontend | ⬜ Not Started |  | Hover effects, fade-in modals, skeleton loaders
FE-16 | Share Feature (WhatsApp) | FE | 🟢 | feature/frontend | Frontend/src/components/Share.jsx | D:\Projects\smart-crop-assistant\Frontend\src\components\ | FE-08 | Frontend | ⬜ Not Started |  | Share result via WhatsApp button
🧪 Testing & Docs
QA-06 | README.md Final Update | QA | 🔴 | main | README.md | D:\Projects\smart-crop-assistant\ | ALL | QA | ⬜ Not Started |  | Badges + setup guide + team table + accuracy results
QA-07 | Video Demo Recording | QA | 🔴 | main | docs/demo-video-link.md | D:\Projects\smart-crop-assistant\Docs\ | TL-05 | QA | ⬜ Not Started |  | 3-5 min walkthrough — crop recommendation + disease detection
QA-08 | Final Documentation Package | QA | 🔴 | main | docs/ | D:\Projects\smart-crop-assistant\Docs\ | ALL | QA | ⬜ Not Started |  | All docs in /Docs — checklist before submission
QA-09 | Security Checklist | QA | 🟡 | main | docs/security-checklist.md | D:\Projects\smart-crop-assistant\Docs\ | BE-15 | QA | ⬜ Not Started |  | No secrets on GitHub, CORS OK, input validation OK
✏️ UI / UX
UX-07 | Presentation Visuals | UX | 🔴 | main | docs/presentation-visuals/ | D:\Projects\smart-crop-assistant\Docs\presentation-visuals\ | AI-13 | UI/UX | ⬜ Not Started |  | Charts: RF 99.55% + CNN 94% + system flow screenshots
Week 5 Summary: Total Tasks = 13 ¦ Already Done = 0 ¦ Remaining = 13

## GitHub Structure
NileCrop — GitHub Repository Structure & Branch Rules
| Branch Name | Who Works On It | Who Can Merge | Protection | Purpose
| main | Team Leader only | Team Leader only | 🔒 FULLY PROTECTED | Production-ready code — never push directly
| dev | All (via PR) | Team Leader | ⚠️ PR Required | Integration testing branch — staging area
| feature/backend | Backend team | Team Leader | ⚠️ PR Required | All FastAPI + PostgreSQL work
| feature/frontend | Frontend team | Team Leader | ⚠️ PR Required | All React + Tailwind + PWA work
| feature/crop-model | AI team | Team Leader | ⚠️ PR Required | Random Forest model + crop recommend endpoint
| feature/disease-model | AI team | Team Leader | ⚠️ PR Required | CNN MobileNetV2 + disease endpoint
📋 Pull Request Workflow — Follow This Every Time
| Step 1 | git add . | Stage your changes
| Step 2 | git commit -m "feat: [TASK-ID] description" | Commit with task ID
| Step 3 | git push origin [your-branch] | Push to your branch
| Step 4 | Go to GitHub → Pull Requests → New PR | Create PR from your branch to main
| Step 5 | Notify Team Leader on WhatsApp | Tell TL the PR is ready for review
| Step 6 | Team Leader reviews + merges | TL merges → task status → 🔒 Locked
| Step 7 | Update Excel status to 🔒 Locked | Mark task as locked in this file

## Task Locking Rules
NileCrop — Task Locking System
HOW TASK LOCKING WORKS
When a task is DONE: | 1. Change status to ✅ Done in this Excel 2. Open Pull Request on GitHub 3. Notify Team Leader on WhatsApp 4. Team Leader reviews the code
After PR is Merged: | 1. Status changes to 🔒 Locked 2. Write the done date in 'Done Date' column 3. The file path on GitHub is now READ-ONLY 4. No one can edit this file without Team Leader approval
What LOCKED means: | The task file is merged into main. If you need to change it → create a new task (hotfix) NEVER edit a locked file directly
Why we lock tasks: | Prevents accidental overwrites Keeps main branch clean and stable Ensures Team Leader reviews everything Creates a clear audit trail
Conflict Prevention: | Each person works on THEIR branch only Two people should NEVER edit the same file If conflict → tell Team Leader IMMEDIATELY Team Leader resolves all merge conflicts
STATUS MEANINGS
⬜ Not Started | Task hasn't been touched yet — waiting
🔄 In Progress | Currently being worked on — update daily in stand-up
✅ Done | Work complete — PR opened — waiting for review
❌ Blocked | Can't continue — tell Team Leader immediately with reason
🔒 Locked | Merged to main — file is read-only — task is complete

## 5-Week Timeline
NileCrop — 5-Week Development Timeline
Week | Focus | TL Deliverables | Backend Deliverables | AI/ML Deliverables | Frontend Deliverables | UX Deliverables | QA Deliverables
Week 1 | Setup + Architecture + Crop Model (Most AI tasks DONE ✅) | GitHub setup ✅ Architecture diagram ✅ ERD design Daily stand-ups | PostgreSQL setup FastAPI skeleton Cities table (60 cities) Weather+Soil APIs | Crop EDA ✅ Preprocessing ✅ RF Model 99.55% ✅ Crop recommend endpoint | — | Color palette User flow ✅ Wireframes planning | requirements.txt
Week 2 | Disease Model + Backend APIs + Frontend Init | Sprint review W1 GitHub Issues W2 Code review | Disease info table (17 records) Request logging City search endpoint Image upload handler | PlantVillage 17-class subset Image preprocessing MobileNetV2 setup Train CNN v1 + v2 (~94%) | React + Vite init Navbar + language toggle Home page hero | Wireframes (4 screens) Hi-Fi mockups | Postman collection prep
Week 3 | Full Integration + Arabic RTL + PWA | Integration test Bug report CORS + security check | Validation + error handling CORS + rate limiting Analytics endpoint | Disease API endpoint Disease lookup (Arabic) TFLite conversion | Crop Modal Disease Modal Connect to backend Result cards Arabic translations (RTL) PWA manifest | App icon + branding Arabic UI review | Manual API testing Postman collection
Week 4 | Testing + Bug Fixes + Deployment | Full integration test Bug triage + assignment | Backend unit tests Deploy on Render Production health check | Model evaluation report Model registry Fix any accuracy issues | Error handling Performance optimization Deploy on Vercel | Production UI vs Figma check | Backend API tests E2E tests Cross-browser testing
Week 5 | Final Polish + Documentation + Presentation | Demo script Feature freeze Final submission to Dr. Eman | Final bug fixes Production health check | Live demo preparation 5 crop + 5 disease tests | UI polish + animations WhatsApp share feature | Presentation visuals Charts + screenshots | README final update Video demo recording Documentation package Security checklist
TOTAL | Total Tasks: 70 ¦ Already Done: 4 ¦ Remaining: 66 ¦ 5 Weeks Duration